## KidMatchEstimates
| Task list | Hours, low-case | Hours, high-case
0.1 | Preparation Tasks
| Research API Doc | 4 | 8
| Add libs, set up project, create repositories | 3 | 5
| Architecture | 4 | 8
| Implement Analytics( Google Analytics) | 1 | 2
0.2 | Common Tasks
| Create base methods for DataBase | 8 | 10
1 | Loading Screen
| Screen layout coding Static Image | 2 | 3
2 | Initial Login
2.1 | Registration parental control
| Screen layout coding Email address and a password 2 text fields (Email & Password) TextFieldEmailError OR ALERT VIEW TextFieldPasswordError OR ALERT VIEW Error in case of wrong input Next Button | 4 | 6
| Handling keyboard appearance | 1 | 2
| Email & Password validation display users errors | 2 | 3
| Store to persistent storage | 1 | 2
2.2 | Choose up to 6 photos
| Screen layout coding Image, Text label, Browse Photos button | 3 | 4
| Browse photo popUp Controller, using external free API QBImagePicker https://github.com/questbeat/QBImagePicker API or https://github.com/B-Sides/ELCImagePickerController | 3 | 5
2.3 | Crop every photo
| Screen layout coding ImageCounter (textView) ImageView(crop Photo), Name(text input), Save&Next button | 6 | 8
| Handling keyboard appearance | 1 | 2
| Crop Image processing | 2 | 3
| Save images to persistent storage | 1 | 2
| Text input validation | 1 | 2
3 | Main Screen
| Screen layout coding menu button, StartGame, Image & Text to Learn More about games Controller | 4 | 6
| Button menu animation | 5 | 8
4 | Menu popUp on Main Screen
| Screen layout coding Small pop up with 2 options | 2 | 3
4.1 | Add Photos
| Screen layout coding ViewController from 2.2 title “Add Family Photos ” and then to ViewController 2.3 with title “Pan and zoom to crop ” | 2 | 3
4.2 | Remove Photos
| Screen layout coding Collection view photos Remove Button | 8 | 10
| Save images to persistent storage | 1 | 2
5 | Buy Now Controller PopUp
| Screen layout coding Button Close top right corner, Little image of a game, TextView with game description, Price textField, Buy Now Button go to Buy Now Controller PopUp Button Close top right, TextView with description, InputField for Parental password, Go button -> Launch Browser with specific link | 8 | 10
| Password validation | 1 | 2
| Handling keyboard appearance | 1 | 2
6 | Game Screen
| Screen layout coding Title on the top, Back Button to menu | 6 | 8
| Collection View | 10 | 12
| Animation | 18 | 20
| Game Logic | 12 | 16
| Animation | 5 | 6
| Congratulation Message | 2 | 3
| Total iOS: | 136 | 192
7 | Generic Design
| Buttons Go, Buy now, Sext & Save, Browse photos, Next | 4 | 6